## Sheet1
AFTER-ACTION REVIEW CONSIDERATION |  |  |  | ORGANIZATIONAL ASSIGNMENT
Improvement Number (Phase/ Function/ #) | Consideration | Recommendation | Assigned Priority Criticallity(H,M,L) | Strategic/ Tactical | Functional Area | POC | POC Email | Start Date | Required Completion Date | Status by percentage | Disposition
Column1 | Column2 | Column3 | Column4 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13
EXAMPLE ONLY M L 17 | Convoy Planning deficiency | Develop Standardized Convoy Plan Template | M | Tactical | Plans-Pol/Doc | Jim Smith | Jsmith @ LAD.COM | 2010-08-01 | 2015-08-01 | 75%
Strengths

## Sheet2
M US&R BR 7 | I 7.0 The initial SR 530 incident objectives were incomplete and hard to measure. There were no fully agreed upon turn back standards established and a priority setting meeting was not attended by all of the necessary decision makers. | 7.1 The IST should encourage and facilitate the AHJ to hold priority-setting meetings consistent with NIMS ICS principles, with all stakeholders actively engaged. | H
|  | 7.2 Objectives should be reviewed and validated each planning cycle and IMT/IST transition period, to maintain relevancy and pertinence | H
|  | 7.3 Turn back standards need to be negotiated, and documented in a signed format as well as communicated, so all stakeholders and parties clearly understand specific exit strategies and options resulting in the same expectations. | H